SwiftTip

Recognise. Reward. Empower.

Operational Plan

& Pilot Validation Plan

How SwiftTip runs — from the first pilot forecourt to operations at scale

Payments · Workers · Dealers · Support · Compliance · The 90-Day Pilot · Scaling

Version 1.1  ·  June 2026  ·  Eastern Cape, South Africa  ·  Confidential

# Contents

# 1. Purpose & How This Plan Is Organised

Operations is where SwiftTip lives or dies. The idea is settled; the risk is execution — payments, trust, onboarding, support, and the discipline to prove the model before scaling. This document covers both how SwiftTip runs day-to-day and the 90-day pilot that validates it.

Part A (Sections 2–9) is the operational plan — the machinery of running the business, written to hold from the pilot through to scale. Part B (Sections 10–12) is the Pilot Validation Plan — the specific 90-day test protocol with success metrics and the stop/adjust/scale decision. Part C (Sections 13–14) covers scaling and the operating calendar.

The Operating Philosophy

Trust is the product. Every operational choice — how fast payouts land, how disputes are handled, how a worker is onboarded — is ultimately about whether a frontline worker, a dealer, and a customer trust SwiftTip. One broken payout or mishandled dispute spreads through a forecourt in hours. Operations exists to make the trust loop turn reliably, every single time.

# 2. Part A — The Payments Operation

The operational heart of SwiftTip. Get this right and the business runs; get it wrong and trust collapses.

## 2.1 The money flow (pass-through, never held)

SwiftTip never holds funds. A licensed payment partner collects the tip from the customer and disburses it to the worker’s own bank account. SwiftTip provides the technology and the instruction — it is not the holder of the money.

Collect → Settle → Disburse

Customer pays R22 (R20 tip + R2 fee) → PSP collects → R20 routes to the worker’s bank, R2 routes to SwiftTip → worker sees “paid to your bank”. Target: split at source, so SwiftTip never touches the worker’s R20. Confirmed in writing with the PSP.

## 2.2 Payout timing — the cost vs trust decision

Three models, trading cost against the strength of the “instant” trust promise. The right answer is decided empirically in the pilot.

| Model | Cost | Trust |
| --- | --- | --- |
| Instant (per-tip) | Highest — one fee per tip | Strongest, but may be unaffordable on micro-tips |
| Same-day batch | Low — one payout, many tips | Strong — “your tips, paid daily”. Likely launch choice. |
| Next-day | Lowest | Weakest — erodes the instant promise |

Operating decision: launch on same-day batch unless the pilot shows it dents trust. Never advertise “instant” unless the product delivers it.

## 2.3 Reconciliation (the unglamorous core)

Daily, match what the PSP settled against what each worker is owed. Semi-manual at pilot scale; automated before scaling past one site — reconciliation breakage is where tipping platforms quietly fail.

- Daily: confirm every tip collected was disbursed; investigate any mismatch immediately.

- Idempotent, logged webhooks: payment confirmations update reliably, retried and logged, so no tip is ever lost.

## 2.4 Failure paths (design before launch)

| Failure | Operational response |
| --- | --- |
| Customer pays, worker bank rejects | Hold in PSP, alert worker to fix details, retry; never silently lose it |
| Duplicate payment | Detect via idempotency key; auto-refund the duplicate |
| Payment succeeds, payout fails | Flag in admin, manual payout within 24h, tell the worker |
| Customer disputes / refund | Defined refund policy; PSP-initiated reversal where valid |
| PSP settlement delay/outage | Proactive worker comms; indemnity clause in PSP contract |

## 2.5 The margin floor

Tip-floor logic: set a minimum tip (e.g. R5–R10) below which a transaction isn’t offered, because a flat cost erodes margin on tiny tips. If the PSP raises fees, recompute the floor — a product rule driven by the cost structure.

# 3. Worker Operations

## 3.1 Onboarding (under 5 minutes, done for them)

- Capture name (as on SA ID), mobile, station, bank, account number — you do it on your phone, on the spot.

- Verify the bank account (via PSP) so the first payout cannot fail.

- Generate and hand over the QR badge immediately — no gap between sign-up and earning.

- Capture POPIA consent for profile, photo, QR and recognition boards.

- Engineer a visible first payout — seed a test tip if needed. The single most important trust moment.

## 3.2 The worker trust FAQ

| Worker asks | Plain answer |
| --- | --- |
| When do I get my money? | Paid to your bank, same day (or instantly, per launch model) |
| Can my employer see what I earn? | No. They see team activity, never your individual earnings |
| Can SwiftTip take my money? | No. Tips go straight to your bank; we never hold it |
| What if I change jobs? | Your profile and history are yours and move with you |
| What if I have no bank account? | We help you open a free/low-cost account (Capitec, TymeBank) |
| Will this affect my salary or tax? | Tips are yours, separate from your wage; we seek a SARS ruling to confirm |

The Worker Promise (say it simply)

“Your tips go to you. Your profile belongs to you. Your employer can see team activity, but your money stays yours.”

## 3.3 Ongoing worker support

- WhatsApp support line per station — right channel for the market; trust-builder and early-warning system.

- Lost QR badge — reprint and reissue same day; the QR ties to the worker ID.

- Worker leaves the station — profile stays with the worker; deactivate the station link, keep their portable identity.

# 4. Dealer & Site Operations

## 4.1 The acquisition motion

- Walk in; ask for the owner by name. Lead with the operator case (less cash, lower crime risk, motivated staff, free 90-day pilot).

- Answer the three approval questions: can you approve this yourself; do uniform rules allow the badge; any existing tipping arrangement.

- Close on the zero-risk pilot: set up the attendants free for 90 days; walk away if it doesn’t work.

## 4.2 Site setup (per forecourt)

- Appoint a SwiftTip Champion — one manager or senior attendant to help onboard and support the team.

- Deploy the collateral — lanyards, pump QR signs, the affiliated-retailer decal, the Employee of the Month board.

- Train the ask + passive prompting — the one-line prompt plus signage that works when the attendant is busy.

- Generate per-station QR links — real URLs (not demo) before printing.

## 4.3 The dealer relationship

The dealer pays nothing and gets the data (Employee of the Month, service activity) as a reason to champion SwiftTip. Keep him an advocate with a monthly station report and a responsive contact. A dealer referring another dealer is the cheapest, strongest growth channel.

# 5. Customer Support, Disputes & Fraud

## 5.1 Support flow

- One channel (WhatsApp + simple form). Generic, non-leaky error messages to users; full errors logged server-side.

- Targets: worker payout issues same-day (trust-critical); customer queries within 24h.

## 5.2 Dispute & refund policy

| Case | Policy |
| --- | --- |
| Wrong worker tipped | Refund or re-route to the correct worker once verified |
| Duplicate / accidental payment | Refund the duplicate automatically |
| Customer dissatisfied | Tips are voluntary gifts; refunds at discretion within a short window |
| Abusive message in tip note | Filter/flag; worker can hide; repeat abusers blocked |

## 5.3 Fraud & abuse controls

- Fake QR / impersonation — only SwiftTip-issued, ID-verified QR codes are valid; the “Verified” cue signals authenticity.

- Suspicious tip patterns — monitor for laundering-style behaviour (large/repeated self-tips); flag and review.

- Rate limits — cap endpoints to prevent abuse and runaway costs.

# 6. Compliance Operations

Trust is the product, so compliance is operational. The running checklist:

| Obligation | Operational action |
| --- | --- |
| Legal entity | SwiftTip (Pty) Ltd registered before real revenue; not under another entity |
| POPIA | Privacy policy live; consent at onboarding; data access controlled |
| Payments status | Written confirmation SwiftTip is technology provider only; PSP holds funds |
| FICA / KYC | ID + bank at onboarding, under the PSP’s KYC umbrella |
| SARS tip treatment | Seek ruling that worker-direct tips are not employer payroll |
| Agreements | Customer terms, worker terms, employer participation agreement |

# 7. Tools & Systems

| Function | Tool | Note |
| --- | --- | --- |
| App / database | Lovable + Supabase | You own the data (the moat) |
| Payments | Ozow (in) / Stitch (out) | Cheapest reliable rail per leg |
| Comms | WhatsApp Business | Right channel for the market |
| Reconciliation | PSP dashboard + admin | Manual at pilot; automate before scale |
| Print | Local printer, matte stock | Per-station QR before printing |

# 8. Security Operations (Staged)

## 8.1 Before worker #1 — the critical four

- Row-Level Security (worker sees only own data; employer only station aggregates)

- No secrets/keys in the frontend

- Server-side validation on anything touching money

- Privacy policy + worker consent flow

## 8.2 Before scale — the hard gate

Secure SDLC, SAST/DAST in the change pipeline, real QA, and a compliant, portable data architecture able to interoperate with banking APIs. The realistic trigger to bring in technical leadership.

# 9. Roles & The First Hire

Solo now — deliberately. You run sales, onboarding, support and reconciliation through the pilot. Stay lean until the model is proven, but know what breaks first.

| What breaks first | The hire it triggers |
| --- | --- |
| Reconciliation & support at multiple sites | An operations/support person (first hire) |
| Security/data maturity before scale & moat | Technical lead / co-founder |
| Dealer acquisition across regions | A regional salesperson |

# 10. Part B — The Pilot Validation Plan

The test that converts strategy into proof. Define success before starting, so the 90 days end in a clear decision, not a vague feeling.

## 10.1 Pilot design

| Parameter | Pilot setting |
| --- | --- |
| Location | Mdantsane Engen cluster, Buffalo City (1–2 sites to start) |
| Workers | ~10–20; best/most-respected attendant onboarded first |
| Duration | 90 days, with a 2-week intercept pre-test first |
| Payment partner | Ozow in / Stitch out (per quotes), same-day batch |
| Fee model | R2 customer-paid; worker keeps 100% |
| Collateral | Lanyard + pump QR + decal + EOTM board; A/B the prompt wording |

## 10.2 The intercept pre-test (do first, under R2,000)

Before launch, ask ~50 customers two framings: “tip R20 + R2 fee, worker keeps 100%” vs “tip R20, worker keeps R18”. Validates the tipping rate — the most sensitive assumption — and the fee framing, before real spend.

# 11. Pilot Metrics & What to Test

The Deciding Metric: Tips per worker per shift

This number decides everything. It tells you whether tipping is a real habit or just a nice idea. Sign-ups can look healthy while this stays near zero — and if it does, there is no business. Track it daily from day one.

## 11.1 The full pilot dashboard

| Metric | Why it matters |
| --- | --- |
| Tips per worker per shift (DECIDER) | Habit or not |
| % workers active (≥1 tip/week) | Real adoption vs vanity sign-ups |
| Customer scans per day | Top-of-funnel interest |
| Scan-to-payment conversion | Is the flow frictionless? |
| Average tip value | Unit economics |
| Payout success rate | Trust — must be ~100% |
| Failed-payment rate | Where the loop breaks |
| Best QR placement | Where to focus collateral |
| Worker & dealer satisfaction | Renewal intent |

## 11.2 The behavioural questions

- The “Ask” vulnerability: does tipping hold up when the attendant is too busy or shy to ask? Test passive prompting vs the verbal ask.

- Payout latency: does same-day (vs instant) settlement dent engagement? Measure, don’t assume.

- Fee tolerance: does the R2 fee suppress tipping on small tips? Watch conversion by tip size.

# 12. The 90-Day Decision: Stop, Adjust, or Scale

The pilot ends in one of three explicit decisions, judged against pre-set thresholds.

| Outcome | What it looks like | Action |
| --- | --- | --- |
| SCALE | Tips/shift healthy & stable; payout ~100%; workers promoting; dealer renews | Pass the gate; expand per geographic plan |
| ADJUST | Promising but a step is weak (placement, conversion, latency) | Fix the loop break; re-test |
| STOP | Tipping rate stays near zero despite fixes | Question the model before more spend |

Set the thresholds before you start

Decide now what “healthy” means — a target tips-per-worker-per-shift, a minimum % of workers active, a payout success rate, and dealer renewal intent. Writing the numbers down before the pilot stops you rationalising a weak result into a false ‘yes’.

# 13. Part C — Operating at Scale

## 13.1 Automate before scaling

- Reconciliation — fully automated

- Onboarding — champion-led or self-service, not founder-led per worker

- Support — templated WhatsApp flows + a support hire

- Collateral — a batch QR/print generator (name + ID → print file)

## 13.2 Multi-site & multi-sector

The same product redeploys across car washes, hospitality, golf and security — but each sector has a different gatekeeper. Scale geography and sector together, ring by ring (Buffalo City → EC corridors → adjacent provinces → national), never faster than support allows. Density beats spread.

## 13.3 The moat layer at scale

Once data is clean and trust proven, activate Phase 3: income-history profiles and partner integrations with banks/lenders/insurers — always via partners, never before the secure-SDLC gate and technical ownership are in place.

# 14. The Operating Calendar

| Cadence | What you do |
| --- | --- |
| Daily | Reconcile tips vs payouts; clear failed payouts within 24h; answer worker support |
| Weekly | Check the north star (tips/worker/shift) — moving or not? If not, what’s broken? |
| Per site | Monthly station report to the dealer; recognise the Employee of the Month |
| Monthly | Review metrics vs thresholds; check phase-gate progress; review the Not-Now list |

The Operational Plan in One Line

Make the trust loop turn reliably every time — pay workers fast and visibly, handle failures and disputes cleanly, onboard in minutes, keep dealers as advocates, prove the model on one forecourt against pre-set thresholds, and automate before you scale.

SwiftTip — Recognise. Reward. Empower.